## Issues Log
Task ID | Features (Stories) | Task | Description | Assigned To | Priority | Time Estimate (days) | Status | Date of Completion | Time Spent (days) | Comments
1 | 팀 프로젝트 주제 선정 | 프로젝트 아이디어 생각 | 팀 프로젝트 주제 선정을 위한 브레인 스토밍 | 팀 전체 | 100 | 5 | Complete | 2017-03-17 | 5
2 | 팀 프로젝트 주제 선정 | idea 관련 자료 조사 | 브레인스토밍에서 나온 아이디어 관련 자료조사 | 팀 전체 | 50 | 5 | Complete | 2017-03-17 | 5
3 | 팀 프로젝트 주제 선정 | idea 최종 선정 및 개선 | 합리적인 아이디어 선정 및 추가 기능 논의 | 팀 전체 | 50 | 2 | Complete | 2017-03-19 | 2
4 | 기존 어플리케이션 조사 | 기존 어플리케이션 Test | 본 프로젝트와 유사한 어플리케이션 설치 및 테스트 | 김태호 | 20 | 1 | Complete | 2017-03-20 | 1
5 | 공모전 조사 | 프로젝트 관련 공모전 조사 | 본 프로젝트와 관련된 공모전 조사 및 참가할 공모전 선정 | 팀 전체 | 30 | 3 | Complete | 2017-03-22 | 3
6 | 스마트워치 선정 | 스마트워치 조사 및 선정 | 스마트워치 플랫폼 조사 및 프로젝트에 적합한 스마트워치 선정 | 부은성 | 20 | 1 | Complete | 2017-03-22 | 1
7 | 시스템 구조 정의 | 시스템 구조 정의 | 프로젝트의 전체 시스템 구조 정의 및 컴포넌트 기능 논의 | 팀 전체 | 60 | 1 | Complete | 2017-03-22 | 1
8 | 컨셉 발표 준비 | 컨셉 발표 ppt 제작 | 컨셉 발표에 필요한 자료 조사 및 ppt 제작 | 임희락 | 40 | 2 | Complete | 2017-03-25 | 2
9 | Prepare for Android | 안드로이드 스튜디오 설치 | 안드로이드 스튜디오 설치 및 필요 패키지 설치 | 김채원 | 20 | 1 | Complete | 2017-03-26 | 1
10 | Prototype of Server | 구글 클라우드 서버 생성 | 구글 클라우드의 Computing Server 생성 | 임희락 | 20 | 1 | Complete | 2017-03-27 | 1
11 | Prototype of SmartWatch | 스마트워치 GUI 구현 | 프로토타입의 스마트워치 GUI 구현 | 부은성 | 20 | 1 | Complete | 2017-03-28 | 1
12 | 스마트폰-서버 통신 | UDP 소켓 통신구축 | 스마트폰에서 서버로 향하는 UDP소켓 통신 구축 | 김채원 | 30 | 2 | Complete | 2017-03-31 | 2
13 | 스마트폰-서버 통신 | 스마트폰 GUI 구현 | 프로토타입의 스마트폰 GUI 구현 | 김채원 | 20 | 1 | Complete | 2017-03-29 | 1
14 | 스마트폰-서버 통신 | 오디오 데이터 스트리밍 | 스마트폰에서 마이크를 통해 들리는 소리를 서버로 스트리밍 | 김채원 | 40 | 2 | Complete | 2017-03-31 | 2.5
15 | 스마트폰-서버 통신 | 서버측 소켓 통신구축 | 다수의 클라이언트 요청을 처리할 수 있는 소켓 연결 구축 | 임희락 | 40 | 3 | Complete | 2017-03-30 | 3.5
16 | sound classification | Urban dataset 학습 | Urban Sound dataset와 tensorflow를 이용하여 머신러닝 | 김태호 | 60 | 3 | Complete | 2017-03-31 | 3
17 | sound classification | sound classification test | 임의의 소리값을 input으로 어떤 분류결과가 나오는지 확인 | 김태호 | 30 | 0.5 | Complete | 2017-04-01 | 0.5
18 | 소리분류 정확도 향상 연구 | 소리 분류 정확도 향상 연구 | 소리 분류를 높이기 위한 방안 연구 | 김태호 | 30 | 3 | Complete | 2017-04-05 | 2
19 | 타이젠 예제코드 테스트 | 타이젠 알림 예제 테스트 및 분석 | 타이젠 알림 예제 테스트 및 분석 | 부은성 | 20 | 3 | Complete | 2017-04-05 | 2
20 | 타이젠 어플 개발방향 비교 | Native App 과 Web APP비교 | 두 type으로 만든 app의 장단점과 본 프로젝트의 적합한 app 선정 | 부은성 | 30 | 2 | Complete | 2017-04-09 | 2
21 | 서버 세부 기능 정의 | 서버 세부기능 정의 | 서버 세부 기능 정의 및 필요한 컴포넌트 조사, 테스트 | 임희락 | 20 | 2 | Complete | 2017-04-07 | 2
22 | 제안 발표 준비 | 제안 발표 준비 | 제안서 작성과 제안 발표에 필요한 사항들 논의 | 팀 전체 | 50 | 4 | Complete | 2017-04-08 | 4.5
23 | 제안서 작성 | 제안서 작성 | 제안서 작성 및 마무리 | 팀 전체 | 40 | 1 | Complete | 2017-04-12 | 1
24 | 멘토님과 미팅 | 멘토님과 미팅 | 본 프로젝트에 대한 설명과 앞으로의 개발방향에 관해 이야기 | 팀 전체 | 60 | 2 | Complete | 2017-04-13 | 2
25 | 공모전 참가서 작성 | 공모전 참가서 작성 | 제9회 소외된 90%를 위한 창의설계 경진대회 참가서 작성 | 김채원 | 50 | 2 | Complete | 2017-04-14 | 2
26
27
28 |  |  | 다수의 클라이언트 요청을 처리할 수 있는 소켓 연결 방식 조사 |  |  | 0.5
29 |  |  | 다중 클라이언트-서버 소켓 연결 테스트 |  |  | 1
30 |  |  | 클라이언트에서 전송하는 오디오 비스트스림을 오디오 확장자 파일로 변환 |  |  | 1
31 |  |  | 클라이언트의 여러 서버 기능 요청에 대한 해시테이블 생성
32 |  |  | 해시테이블이 나타내는 각 기능에 대해여 echo function 구현
33 |  |  | echo function으로 클라이언트와 기능간 연결 테스트
34 |  |  | 서버에 Dummy database file생성 및 SQLite 테스트
35 |  |  | 시스템 시작단계에서 database file 유뮤 확인 및 서버 프로그램과 연동
36
37 |  |  | 딥러닝을 통해 구한 classifier로 오디오 파일의 라벨 결과 구하기
38 |  |  | 오디오 파일 라벨 결과 클라이언트로 전송
39 |  |  | 사용자 정보 처리 및 데이터베이스화 기능 구현
40 |  |  | 사용자 추가 오디오 파일과 지정 라벨을 저장 및 데이터베이스화
41 |  |  | 서버-클라이언트 간 연동 연동 테스트 및 다중 사용자 처리 테스트
42
43 |  |  | 클라이언트의 버그리포트 요청을 데이터메니저 또는 개발자등에게 메일로 전달.
44
45 |  |  | 서버 코드 최적화
46 |  |  | 클라이언트-서버 간 기능 전수 테스트 및 버그 수정
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300

## Iteration 1
Iteration 1
| Start Date | 2017-03-13
| End Date | 2017-03-27
| # of Developers | 4
| Efficiency Factor | 0.5
| Work Days | 11
| Man Days | 44
| Effective Man Days | 22
| m - Ideal Remaing Effort | -2
| Total Tasks Assigned | 22
| Available Time - Assigned time | 0
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
1 | 프로젝트 아이디어 생각 | 5 | Complete | 2017-03-17 | 5 | 5 | 프로젝트 아이디어 생각 | Complete | 2017-03-17 | 5 | 22 | 2017-03-13 | 1 | 22 | 22 | 0 | 0 |  | 2017-04-28
2 | idea 관련 자료 조사 | 5 | Complete | 2017-03-17 | 5 | 5 | idea 관련 자료 조사 | Complete | 2017-03-17 | 5 | 20 | 2017-03-14 | 2 | 20 | 22 | 0 | 4 | 0 | 30
3 | idea 최종 선정 및 개선 | 2 | Complete | 2017-03-19 | 2 | 2 | idea 최종 선정 및 개선 | Complete | 2017-03-19 | 2 | 18 | 2017-03-15 | 3 | 18 | 22 | 0 | 8 | 0
4 | 기존 어플리케이션 Test | 1 | Complete | 2017-03-20 | 1 | 1 | 기존 어플리케이션 Test | Complete | 2017-03-20 | 1 | 16 | 2017-03-16 | 4 | 16 | 22 | 0 | 12 | 0
5 | 프로젝트 관련 공모전 조사 | 3 | Complete | 2017-03-22 | 3 | 3 | 프로젝트 관련 공모전 조사 | Complete | 2017-03-22 | 3 | 14 | 2017-03-17 | 5 | 14 | 22 | 0 | 16 | 0
6 | 스마트워치 조사 및 선정 | 1 | Complete | 2017-03-22 | 1 | 1 | 스마트워치 조사 및 선정 | Complete | 2017-03-22 | 1 | 12 | 2017-03-20 | 6 | 12 | 10 | 12 | 20 | 0.6
7 | 시스템 구조 정의 | 1 | Complete | 2017-03-22 | 1 | 1 | 시스템 구조 정의 | Complete | 2017-03-22 | 1 | 10 | 2017-03-21 | 7 | 10 | 9 | 13 | 24 | 0.54
8 | 컨셉 발표 ppt 제작 | 2 | Complete | 2017-03-25 | 2 | 2 | 컨셉 발표 ppt 제작 | Complete | 2017-03-25 | 2 | 8 | 2017-03-22 | 8 | 8 | 9 | 13 | 28 | 0.46
9 | 안드로이드 스튜디오 설치 | 1 | Complete | 2017-03-26 | 1 | 1 | 안드로이드 스튜디오 설치 | Complete | 2017-03-26 | 1 | 6 | 2017-03-23 | 9 | 6 | 4 | 18 | 32 | 0.56
10 | 구글 클라우드 서버 생성 | 1 | Complete | 2017-03-27 | 1 | 1 | 구글 클라우드 서버 생성 | Complete | 2017-03-27 | 1 | 4 | 2017-03-24 | 10 | 4 | 4 | 18 | 36 | 0.5
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | 2017-03-27 | 11 | 2 | 1 | 21 | 40 | 0.53
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-03-28 | 12 | 0 | 0 | 22 | 44 | 0.5
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2 | 2017-03-29 | 13 | 0 | 0 | 22 | 48 | 0.46
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -4 | 2017-03-30 | 14 | 0 | 0 | 22 | 52 | 0.42
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -6 | 2017-03-31 | 15 | 0 | 0 | 22 | 56 | 0.39
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8 | 2017-04-03 | 16 | 0 | 0 | 22 | 60 | 0.37
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -10 | 2017-04-04 | 17 | 0 | 0 | 22 | 64 | 0.34
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -12 | 2017-04-05 | 18 | 0 | 0 | 22 | 68 | 0.32
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14 | 2017-04-06 | 19 | 0 | 0 | 22 | 72 | 0.31
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16 | 2017-04-07 | 20 | 0 | 0 | 22 | 76 | 0.29
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -18 | 2017-04-10 | 21 | 0 | 0 | 22 | 80 | 0.28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -20 | 2017-04-11 | 22 | 0 | 0 | 22 | 84 | 0.26
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22 | 2017-04-12 | 23 | 0 | 0 | 22 | 88 | 0.25
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -24 | 2017-04-13 | 24 | 0 | 0 | 22 | 92 | 0.24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -26 | 2017-04-14 | 25 | 0 | 0 | 22 | 96 | 0.23
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28 | 2017-04-17 | 26 | 0 | 0 | 22 | 100 | 0.22
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -30 | 2017-04-18 | 27 | 0 | 0 | 22 | 104 | 0.21
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -32 | 2017-04-19 | 28 | 0 | 0 | 22 | 108 | 0.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -34 | 2017-04-27 | 29 | 0 | 0 | 22 | 112 | 0.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36 | 2017-04-28 | 30 | 0 | 0 | 22 | 116 | 0.19
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 24
Formulas:
Date of Completion = IF(ISERROR([get date of completion]),"",[get date of completion])
get date of completion = VLOOKUP([Task Id], 'Issues Log'!$B3:J302, 9, FALSE)
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 2
Iteration 1
| Start Date | 2017-03-28
| End Date | 2017-04-11
| # of Developers | 4
| Efficiency Factor | 0.6
| Work Days | 11
| Man Days | 44
| Effective Man Days | 26.4
| m - Ideal Remaing Effort | -2.4
| Total Tasks Assigned | 26.5
| Available Time - Assigned time | -0.1
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
11 | 스마트워치 GUI 구현 | 1 | Complete | 2017-03-28 | 1 | 1 | 스마트워치 GUI 구현 | Complete | 2017-03-28 | 1 | 26.4 | 2017-03-28 | 1 | 26.4 | 26.4 | 0 | 0 |  | 2017-04-28
12 | UDP 소켓 통신구축 | 2 | Complete | 2017-03-31 | 2 | 2 | UDP 소켓 통신구축 | Complete | 2017-03-31 | 2 | 24 | 2017-03-29 | 2 | 24 | 25.4 | 1 | 4 | 0.25 | 19
13 | 스마트폰 GUI 구현 | 1 | Complete | 2017-03-29 | 1 | 1 | 스마트폰 GUI 구현 | Complete | 2017-03-29 | 1 | 21.6 | 2017-03-30 | 3 | 21.6 | 24.4 | 2 | 8 | 0.25
14 | 오디오 데이터 스트리밍 | 2 | Complete | 2017-03-31 | 2.5 | 2 | 오디오 데이터 스트리밍 | Complete | 2017-03-31 | 2.5 | 19.2 | 2017-03-31 | 4 | 19.2 | 20.9 | 5.5 | 12 | 0.46
15 | 서버측 소켓 통신구축 | 3 | Complete | 2017-03-30 | 3.5 | 3 | 서버측 소켓 통신구축 | Complete | 2017-03-30 | 3.5 | 16.8 | 2017-04-03 | 5 | 16.8 | 12.9 | 13.5 | 16 | 0.84
16 | Urban dataset 학습 | 3 | Complete | 2017-03-31 | 3 | 3 | Urban dataset 학습 | Complete | 2017-03-31 | 3 | 14.4 | 2017-04-04 | 6 | 14.4 | 12.9 | 13.5 | 20 | 0.68
17 | sound classification test | 0.5 | Complete | 2017-04-01 | 0.5 | 0.5 | sound classification test | Complete | 2017-04-01 | 0.5 | 12 | 2017-04-05 | 7 | 12 | 12.9 | 13.5 | 24 | 0.56
18 | 소리 분류 정확도 향상 연구 | 3 | Complete | 2017-04-05 | 2 | 3 | 소리 분류 정확도 향상 연구 | Complete | 2017-04-05 | 2 | 9.6 | 2017-04-06 | 8 | 9.6 | 8.9 | 17.5 | 28 | 0.63
19 | 타이젠 알림 예제 테스트 및 분석 | 3 | Complete | 2017-04-05 | 2 | 3 | 타이젠 알림 예제 테스트 및 분석 | Complete | 2017-04-05 | 2 | 7.2 | 2017-04-07 | 9 | 7.2 | 8.9 | 17.5 | 32 | 0.55
20 | Native App 과 Web APP비교 | 2 | Complete | 2017-04-09 | 2 | 2 | Native App 과 Web APP비교 | Complete | 2017-04-09 | 2 | 4.8 | 2017-04-10 | 10 | 4.8 | 0.4 | 26 | 36 | 0.72
21 | 서버 세부기능 정의 | 2 | Complete | 2017-04-07 | 2 | 2 | 서버 세부기능 정의 | Complete | 2017-04-07 | 2 | 2.4 | 2017-04-11 | 11 | 2.4 | 0.4 | 26 | 40 | 0.65
22 | 제안 발표 준비 | 4 | Complete | 2017-04-08 | 4.5 | 4 | 제안 발표 준비 | Complete | 2017-04-08 | 4.5 | 0 | 2017-04-12 | 12 | 0 | 0.4 | 26 | 44 | 0.59
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.4 | 2017-04-13 | 13 | 0 | 0.4 | 26 | 48 | 0.54
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -4.8 | 2017-04-14 | 14 | 0 | 0.4 | 26 | 52 | 0.5
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -7.2 | 2017-04-17 | 15 | 0 | 0.4 | 26 | 56 | 0.46
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -9.6 | 2017-04-18 | 16 | 0 | 0.4 | 26 | 60 | 0.43
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -12 | 2017-04-19 | 17 | 0 | 0.4 | 26 | 64 | 0.41
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14.4 | 2017-04-27 | 18 | 0 | 0.4 | 26 | 68 | 0.38
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-04-28 | 19 | 0 | 0.4 | 26 | 72 | 0.36
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.2 | 2017-05-01 | 20 | 0 | 0.4 | 26 | 76 | 0.34
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -21.6 | 2017-05-02 | 21 | 0 | 0.4 | 26 | 80 | 0.33
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -24 | 2017-05-04 | 22 | 0 | 0.4 | 26 | 84 | 0.31
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -26.4 | 2017-05-08 | 23 | 0 | 0.4 | 26 | 88 | 0.3
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28.8 | 2017-05-10 | 24 | 0 | 0.4 | 26 | 92 | 0.28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -31.2 | 2017-05-11 | 25 | 0 | 0.4 | 26 | 96 | 0.27
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -33.6 | 2017-05-12 | 26 | 0 | 0.4 | 26 | 100 | 0.26
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36 | 2017-05-15 | 27 | 0 | 0.4 | 26 | 104 | 0.25
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -38.4 | 2017-05-16 | 28 | 0 | 0.4 | 26 | 108 | 0.24
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -40.8 | 2017-05-17 | 29 | 0 | 0.4 | 26 | 112 | 0.23
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -43.2 | 2017-05-18 | 30 | 0 | 0.4 | 26 | 116 | 0.22
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28.8
Formulas:
Date of Completion = IF(ISERROR([get date of completion]),"",[get date of completion])
get date of completion = VLOOKUP([Task Id], 'Issues Log'!$B3:J302, 9, FALSE)
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 3
Iteration 1
| Start Date | 2017-04-12
| End Date | 2017-04-26
| # of Developers | 4
| Efficiency Factor | 0.3
| Work Days | 6
| Man Days | 24
| Effective Man Days | 7.2
| m - Ideal Remaing Effort | -1.2
| Total Tasks Assigned | 3
| Available Time - Assigned time | 4.2
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
23 | 제안서 작성 | 1 | Complete | 2017-04-12 | 1 | 1 | 제안서 작성 | Complete | 2017-04-12 | 1 | 7.2 | 2017-04-12 | 1 | 7.2 | 7.2 | 0 | 0 |  | 2017-04-28
24 | 멘토님과 미팅 | 2 | Complete | 2017-04-13 | 2 | 2 | 멘토님과 미팅 | Complete | 2017-04-13 | 2 | 6 | 2017-04-13 | 2 | 6 | 6.2 | 1 | 4 | 0.25 | 8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 4.8 | 2017-04-14 | 3 | 4.8 | 4.2 | 3 | 8 | 0.38
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 3.6 | 2017-04-17 | 4 | 3.6 | 4.2 | 3 | 12 | 0.25
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2.4 | 2017-04-18 | 5 | 2.4 | 4.2 | 3 | 16 | 0.19
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 1.2 | 2017-04-19 | 6 | 1.2 | 4.2 | 3 | 20 | 0.15
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-04-27 | 7 | 0 | 4.2 | 3 | 24 | 0.13
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -1.2 | 2017-04-28 | 8 | 0 | 4.2 | 3 | 28 | 0.11
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.4 | 2017-05-01 | 9 | 0 | 4.2 | 3 | 32 | 0.09
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -3.6 | 2017-05-02 | 10 | 0 | 4.2 | 3 | 36 | 0.08
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -4.8 | 2017-05-04 | 11 | 0 | 4.2 | 3 | 40 | 0.08
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -6 | 2017-05-08 | 12 | 0 | 4.2 | 3 | 44 | 0.07
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -7.2 | 2017-05-10 | 13 | 0 | 4.2 | 3 | 48 | 0.06
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8.4 | 2017-05-11 | 14 | 0 | 4.2 | 3 | 52 | 0.06
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -9.6 | 2017-05-12 | 15 | 0 | 4.2 | 3 | 56 | 0.05
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -10.8 | 2017-05-15 | 16 | 0 | 4.2 | 3 | 60 | 0.05
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -12 | 2017-05-16 | 17 | 0 | 4.2 | 3 | 64 | 0.05
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -13.2 | 2017-05-17 | 18 | 0 | 4.2 | 3 | 68 | 0.04
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14.4 | 2017-05-18 | 19 | 0 | 4.2 | 3 | 72 | 0.04
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -15.6 | 2017-05-19 | 20 | 0 | 4.2 | 3 | 76 | 0.04
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-05-22 | 21 | 0 | 4.2 | 3 | 80 | 0.04
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -18 | 2017-05-23 | 22 | 0 | 4.2 | 3 | 84 | 0.04
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.2 | 2017-05-24 | 23 | 0 | 4.2 | 3 | 88 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -20.4 | 2017-05-25 | 24 | 0 | 4.2 | 3 | 92 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -21.6 | 2017-05-26 | 25 | 0 | 4.2 | 3 | 96 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22.8 | 2017-05-29 | 26 | 0 | 4.2 | 3 | 100 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -24 | 2017-05-30 | 27 | 0 | 4.2 | 3 | 104 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -25.2 | 2017-05-31 | 28 | 0 | 4.2 | 3 | 108 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -26.4 | 2017-06-01 | 29 | 0 | 4.2 | 3 | 112 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -27.6 | 2017-06-02 | 30 | 0 | 4.2 | 3 | 116 | 0.03
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4
Formulas:
Date of Completion = IF(ISERROR([get date of completion]),"",[get date of completion])
get date of completion = VLOOKUP([Task Id], 'Issues Log'!$B3:J302, 9, FALSE)
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 4
Iteration 1
| Start Date | 2017-04-27
| End Date | 2017-05-11
| # of Developers | 4
| Efficiency Factor | 0.7
| Work Days | 8
| Man Days | 32
| Effective Man Days | 22.4
| m - Ideal Remaing Effort | -2.8
| Total Tasks Assigned | 0
| Available Time - Assigned time | 22.4
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 22.4 | 2017-04-27 | 1 | 22.4 | 22.4 | 0 | 0 |  | 2017-04-28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 19.6 | 2017-04-28 | 2 | 19.6 | 22.4 | 0 | 4 | 0 | 2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8 | 2017-05-01 | 3 | 16.8 | 22.4 | 0 | 8 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 14 | 2017-05-02 | 4 | 14 | 22.4 | 0 | 12 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 11.2 | 2017-05-04 | 5 | 11.2 | 22.4 | 0 | 16 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4 | 2017-05-08 | 6 | 8.4 | 22.4 | 0 | 20 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6 | 2017-05-10 | 7 | 5.6 | 22.4 | 0 | 24 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2.8 | 2017-05-11 | 8 | 2.8 | 22.4 | 0 | 28 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-05-12 | 9 | 0 | 22.4 | 0 | 32 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.8 | 2017-05-15 | 10 | 0 | 22.4 | 0 | 36 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -5.6 | 2017-05-16 | 11 | 0 | 22.4 | 0 | 40 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8.4 | 2017-05-17 | 12 | 0 | 22.4 | 0 | 44 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -11.2 | 2017-05-18 | 13 | 0 | 22.4 | 0 | 48 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14 | 2017-05-19 | 14 | 0 | 22.4 | 0 | 52 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-05-22 | 15 | 0 | 22.4 | 0 | 56 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.6 | 2017-05-23 | 16 | 0 | 22.4 | 0 | 60 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22.4 | 2017-05-24 | 17 | 0 | 22.4 | 0 | 64 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -25.2 | 2017-05-25 | 18 | 0 | 22.4 | 0 | 68 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28 | 2017-05-26 | 19 | 0 | 22.4 | 0 | 72 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -30.8 | 2017-05-29 | 20 | 0 | 22.4 | 0 | 76 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -33.6 | 2017-05-30 | 21 | 0 | 22.4 | 0 | 80 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36.4 | 2017-05-31 | 22 | 0 | 22.4 | 0 | 84 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -39.2 | 2017-06-01 | 23 | 0 | 22.4 | 0 | 88 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -42 | 2017-06-02 | 24 | 0 | 22.4 | 0 | 92 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -44.8 | 2017-06-05 | 25 | 0 | 22.4 | 0 | 96 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -47.6 | 2017-06-07 | 26 | 0 | 22.4 | 0 | 100 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -50.4 | 2017-06-08 | 27 | 0 | 22.4 | 0 | 104 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -53.2 | 2017-06-09 | 28 | 0 | 22.4 | 0 | 108 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -56 | 2017-06-12 | 29 | 0 | 22.4 | 0 | 112 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -58.8 | 2017-06-13 | 30 | 0 | 22.4 | 0 | 116 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2
Formulas:
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 5
Iteration 1
| Start Date | 2017-05-12
| End Date | 2017-05-26
| # of Developers | 4
| Efficiency Factor | 0.7
| Work Days | 11
| Man Days | 44
| Effective Man Days | 30.8
| m - Ideal Remaing Effort | -2.8
| Total Tasks Assigned | 0
| Available Time - Assigned time | 30.8
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 30.8 | 2017-05-12 | 1 | 30.8 | 30.8 | 0 | 0 |  | 2017-04-28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28 | 2017-05-15 | 2 | 28 | 30.8 | 0 | 4 | 0 | -8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2 | 2017-05-16 | 3 | 25.2 | 30.8 | 0 | 8 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 22.4 | 2017-05-17 | 4 | 22.4 | 30.8 | 0 | 12 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 19.6 | 2017-05-18 | 5 | 19.6 | 30.8 | 0 | 16 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8 | 2017-05-19 | 6 | 16.8 | 30.8 | 0 | 20 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 14 | 2017-05-22 | 7 | 14 | 30.8 | 0 | 24 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 11.2 | 2017-05-23 | 8 | 11.2 | 30.8 | 0 | 28 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4 | 2017-05-24 | 9 | 8.4 | 30.8 | 0 | 32 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6 | 2017-05-25 | 10 | 5.6 | 30.8 | 0 | 36 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2.8 | 2017-05-26 | 11 | 2.8 | 30.8 | 0 | 40 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-05-29 | 12 | 0 | 30.8 | 0 | 44 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.8 | 2017-05-30 | 13 | 0 | 30.8 | 0 | 48 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -5.6 | 2017-05-31 | 14 | 0 | 30.8 | 0 | 52 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8.4 | 2017-06-01 | 15 | 0 | 30.8 | 0 | 56 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -11.2 | 2017-06-02 | 16 | 0 | 30.8 | 0 | 60 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14 | 2017-06-05 | 17 | 0 | 30.8 | 0 | 64 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-06-07 | 18 | 0 | 30.8 | 0 | 68 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.6 | 2017-06-08 | 19 | 0 | 30.8 | 0 | 72 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22.4 | 2017-06-09 | 20 | 0 | 30.8 | 0 | 76 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -25.2 | 2017-06-12 | 21 | 0 | 30.8 | 0 | 80 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28 | 2017-06-13 | 22 | 0 | 30.8 | 0 | 84 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -30.8 | 2017-06-14 | 23 | 0 | 30.8 | 0 | 88 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -33.6 | 2017-06-15 | 24 | 0 | 30.8 | 0 | 92 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36.4 | 2017-06-16 | 25 | 0 | 30.8 | 0 | 96 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -39.2 | 2017-06-26 | 26 | 0 | 30.8 | 0 | 100 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -42 | 2017-06-27 | 27 | 0 | 30.8 | 0 | 104 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -44.8 | 2017-06-28 | 28 | 0 | 30.8 | 0 | 108 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -47.6 | 2017-06-29 | 29 | 0 | 30.8 | 0 | 112 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -50.4 | 2017-06-30 | 30 | 0 | 30.8 | 0 | 116 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 33.6
Formulas:
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 6
Iteration 1
| Start Date | 2017-05-27
| End Date | 2017-06-11
| # of Developers | 4
| Efficiency Factor | 0.7
| Work Days | 9
| Man Days | 36
| Effective Man Days | 25.2
| m - Ideal Remaing Effort | -2.8
| Total Tasks Assigned | 0
| Available Time - Assigned time | 25.2
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 25.2 | 2017-05-27 | 1 | 25.2 | 25.2 | 0 | 0 |  | 2017-04-28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 22.4 | 2017-05-29 | 2 | 22.4 | 25.2 | 0 | 4 | 0 | -18
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 19.6 | 2017-05-30 | 3 | 19.6 | 25.2 | 0 | 8 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8 | 2017-05-31 | 4 | 16.8 | 25.2 | 0 | 12 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 14 | 2017-06-01 | 5 | 14 | 25.2 | 0 | 16 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 11.2 | 2017-06-02 | 6 | 11.2 | 25.2 | 0 | 20 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4 | 2017-06-05 | 7 | 8.4 | 25.2 | 0 | 24 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6 | 2017-06-07 | 8 | 5.6 | 25.2 | 0 | 28 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2.8 | 2017-06-08 | 9 | 2.8 | 25.2 | 0 | 32 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-06-09 | 10 | 0 | 25.2 | 0 | 36 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.8 | 2017-06-12 | 11 | 0 | 25.2 | 0 | 40 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -5.6 | 2017-06-13 | 12 | 0 | 25.2 | 0 | 44 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8.4 | 2017-06-14 | 13 | 0 | 25.2 | 0 | 48 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -11.2 | 2017-06-15 | 14 | 0 | 25.2 | 0 | 52 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14 | 2017-06-16 | 15 | 0 | 25.2 | 0 | 56 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-06-26 | 16 | 0 | 25.2 | 0 | 60 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.6 | 2017-06-27 | 17 | 0 | 25.2 | 0 | 64 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22.4 | 2017-06-28 | 18 | 0 | 25.2 | 0 | 68 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -25.2 | 2017-06-29 | 19 | 0 | 25.2 | 0 | 72 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28 | 2017-06-30 | 20 | 0 | 25.2 | 0 | 76 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -30.8 | 2017-07-03 | 21 | 0 | 25.2 | 0 | 80 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -33.6 | 2017-07-04 | 22 | 0 | 25.2 | 0 | 84 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36.4 | 2017-07-05 | 23 | 0 | 25.2 | 0 | 88 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -39.2 | 2017-07-06 | 24 | 0 | 25.2 | 0 | 92 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -42 | 2017-07-07 | 25 | 0 | 25.2 | 0 | 96 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -44.8 | 2017-07-10 | 26 | 0 | 25.2 | 0 | 100 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -47.6 | 2017-07-11 | 27 | 0 | 25.2 | 0 | 104 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -50.4 | 2017-07-12 | 28 | 0 | 25.2 | 0 | 108 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -53.2 | 2017-07-13 | 29 | 0 | 25.2 | 0 | 112 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -56 | 2017-07-14 | 30 | 0 | 25.2 | 0 | 116 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 28
Formulas:
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Iteration 7
Iteration 1
| Start Date | 2017-06-12
| End Date | 2017-06-23
| # of Developers | 4
| Efficiency Factor | 0.7
| Work Days | 5
| Man Days | 20
| Effective Man Days | 14
| m - Ideal Remaing Effort | -2.8
w
| Total Tasks Assigned | 0
| Available Time - Assigned time | 14
Task Id | Title | Estimate | Status | Date of Completion | Time Spent | Get Estimate | Get Title | Get Status | get date of completion | Get Time spent | Get ideal tasks remaining | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Today / Workday
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 14 | 2017-06-12 | 1 | 14 | 14 | 0 | 0 |  | 2017-04-28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 11.2 | 2017-06-13 | 2 | 11.2 | 14 | 0 | 4 | 0 | -28
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 8.4 | 2017-06-14 | 3 | 8.4 | 14 | 0 | 8 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6 | 2017-06-15 | 4 | 5.6 | 14 | 0 | 12 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 2.8 | 2017-06-16 | 5 | 2.8 | 14 | 0 | 16 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 2017-06-26 | 6 | 0 | 14 | 0 | 20 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -2.8 | 2017-06-27 | 7 | 0 | 14 | 0 | 24 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -5.6 | 2017-06-28 | 8 | 0 | 14 | 0 | 28 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -8.4 | 2017-06-29 | 9 | 0 | 14 | 0 | 32 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -11.2 | 2017-06-30 | 10 | 0 | 14 | 0 | 36 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -14 | 2017-07-03 | 11 | 0 | 14 | 0 | 40 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -16.8 | 2017-07-04 | 12 | 0 | 14 | 0 | 44 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -19.6 | 2017-07-05 | 13 | 0 | 14 | 0 | 48 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -22.4 | 2017-07-06 | 14 | 0 | 14 | 0 | 52 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -25.2 | 2017-07-07 | 15 | 0 | 14 | 0 | 56 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -28 | 2017-07-10 | 16 | 0 | 14 | 0 | 60 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -30.8 | 2017-07-11 | 17 | 0 | 14 | 0 | 64 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -33.6 | 2017-07-12 | 18 | 0 | 14 | 0 | 68 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -36.4 | 2017-07-13 | 19 | 0 | 14 | 0 | 72 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -39.2 | 2017-07-14 | 20 | 0 | 14 | 0 | 76 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -42 | 2017-07-17 | 21 | 0 | 14 | 0 | 80 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -44.8 | 2017-07-18 | 22 | 0 | 14 | 0 | 84 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -47.6 | 2017-07-19 | 23 | 0 | 14 | 0 | 88 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -50.4 | 2017-07-20 | 24 | 0 | 14 | 0 | 92 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -53.2 | 2017-07-21 | 25 | 0 | 14 | 0 | 96 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -56 | 2017-07-24 | 26 | 0 | 14 | 0 | 100 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -58.8 | 2017-07-25 | 27 | 0 | 14 | 0 | 104 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -61.6 | 2017-07-26 | 28 | 0 | 14 | 0 | 108 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -64.4 | 2017-07-27 | 29 | 0 | 14 | 0 | 112 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | -67.2 | 2017-07-28 | 30 | 0 | 14 | 0 | 116 | 0
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | 16.8
Formulas:
Work Date = WORKDAY(D3,([Work Days]-1),Holidays!$C5:C100)
Note on B23: Add the task ID's below

## Members
Insert new member(s) right after the last member whenver needed
부은성
김채원
임희락
김태호
팀 전체

## Holidays
공휴일 목록
이름 | 날짜
중간고사 | 2017-04-20
중간고사 | 2017-04-21
중간고사 | 2017-04-22
중간고사 | 2017-04-23
중간고사 | 2017-04-24
중간고사 | 2017-04-25
중간고사 | 2017-04-26
석가탄신일 | 2017-05-03
어린이날 | 2017-05-05
대통령 선거 | 2017-05-09
현충일 | 2017-06-06
기말고사 | 2017-06-19
기말고사 | 2017-06-20
기말고사 | 2017-06-21
기말고사 | 2017-06-22
기말고사 | 2017-06-23